## Sheet1
Scrum Meetings
Group -7
Person | Question | Meeting 1-17/02/20 | Meeting 2 - 19/03/20 | Meeting 3 - 28/02/20 | Meeting 4 - 02/03/20 | Meeting 5- 04/03/20 | Meeting 6- 06/02/20 | Meeting 7- 09/03/20 | Meeting 8- 11/03/20 | Meeting 9- 12/03/20 | Meeting 10- 15/03/20
Muskan | What did you do yesterday? | DFD - identified inputs and outputs of the system and structured level 0 dfd | DFD- identified user processes of level 1 and relationship with user entity | DFD - Level 1 made | DFD - level 2 of organizer processes and finalized level 1 | Finalized DFD with all levels | AD - Made organizer part and add event AD | Finalized AD diagram | Test cases for 'interested club' - user requirement | Finalized interested club module test cases requirements | Finalzed test cases for 'register for events' module
| What will you work on today? | DFD- identifying the processs in level 1 of user | Making level 1 DFD | DFD- Remaking of level 1 after doubts and level 2 of organizer processes | DFD - finalizing the DFD | AD- Activity Diagramm - organizer part making | AD- finalizing AD | Test cases for User interaction module - select interested clubs | Finalizing 'interested user' test cases | Test cases for 'register for events' - user module 2 | Finalizing Test cases for user module 2
| Do you have any obstacles? | Ambiguous nature of user and organizer as inputs to the system | No such obstacles faced | Geting data from datastore; numbers to be written on parallel processes | DFD - input and output of level 2 processes; | Online Tool related problems | doubts in forming actvity diagram of an activty | No obstacles as such for AD diagram | confusion in new user and old user interested club filling requirement, min and max number of clubs discussion | No such obstacles, doubts resolved | Any test case needed for validation status after registering; Multiple clicks register button from same user should be validated for errors?
Arpit | What did you do yesterday? | Use case - Identify Actors | Use case - Identify use case for individual actor | State diagram - Identify the state | State diagram - identify composition state | State diagram - identify starting and endings of the states | State diagram - Draw diagram on paper | Finalizing State diagram | Define user interface module and functional requirement | Define the test cases for all the user interface requirement | Finalizing functional requirement for the view module
| What will you work on today? | Use case - Identify use case for all individual actors | Use case - Incoorporated include functionality within use cases | State diagram - Identify transition | State diagram - identify starting and endings of the states | State diagram - finalize all the state and flow of all the state transition | State diagram - send the diagram for drawing | Business Requirement for user interface | Define the test cases for all the user interface requirement | Business Requirement for View module | define test cases for give access of the screen to organizer
| Do you have any obstacles? | Use case - Can event be the Actor | Use case - can backgroud process part of the use case | Can background process be state? | How to handel state backward compatibility | No such obstacles faced | No such obstacles faced | User can access system in any plotform | No such obstacles | Problem of diffrentiate screen user and organizer | No such obstacles
Vaishwi | What did you do yesterday? | Use case - Define the Scenario | Use case - Incoorporated include functionality within use cases | Use case - Finalizing remianing thing | Use case cmpleted in tool | AD - Made user part diagram | AD - made AD of modify and delete events | finalizing AD | Define the User login module and define test cases | Define the organizer login module and define test cases | Finalizing all requirement for the view module
| What will you work on today? | Use case - Identify Actors | Use case - Finalizing remianing thing | Use Case- Draw diagram in the online tool | AD- Activity Diagramm - user part making | AD- expanding modify/delete events into new activty diagram | AD - finalizing AD | Business Requirement for Login module | Define the organizer login module and define test cases | Functional reuirement for View module | define test cases for give access of the screen to all user
| Do you have any obstacles? | Take care of each small requirement | No such obstacles faced | No such obstacles faced | ,No such obstacles faced | doubts in making multiple activity diagrams | doubts in forming actvity diagram of an activty | User includes which student and staff both | No such obstacles | Give access of the screen view to all user and organizer | No such obstacles
Sumit | What did you do yesterday? | Made level 0 dfd and researched on number of levels of dfd | Identified organizer processes of level 1 and relationship with organizer entity | Made Level 1 DFD | Level 2 of user processes | made Level 2 for organizer processes | Validation of DFD | Finalizing DFD | defining organizers interaction | definined the working of modifying an event | defined viewing registered users for event
| What will you work on today? | Identifying the user processs in level 1 of organizer | Making level 1 DFD | Level 2 user process - view events, authorize user | Level 2 organizer process - add,modify,delete events | review and validate Level 2 DFD | Build DFD on Visual Paradigm Tool | designing the attributes to fill while adding an event, if any entry field is empty | while modifying if more than one field is changed | viewing the number of registrations after event modification | Finalize view of registered users
| Do you have any obstacles? | No such obstacles faced | organizing level 1 structure | Representing different category of events and conditional statements in DFD | Representing different views of different category of events in DFD | No such obstacles faced | Tool related issues | No such obstacles | no such obstacles | flow of updating modified events to users | changing views of registered users in case of modification or cancelation
Krinali | What did you do yesterday? | Identify the enities of the application | List out the attributes of the entities | Identify the relationships between entities | Formation of complete ER diagram | Final rewiew to ER for data redudancy | Took a group review on the final ER | Completing the ER | defining organizers interaction | defining the working of adding the event | defining the working of deleting the event
| What will you work on today? | what are the attributes if the entities of the entities | Identify the relationships between the entities | Formation of complete ER diagram | Final review to ER-diagram for decreasing redudancy | Group rewiew on ER | Building the ER for final presentation on Visual paradigm | building template for adding event, display on screen | while modifying if one of the field is changed | if event deleted and no reason provided
| Do you have any obstacles? | identifying weak and strong entities | Removed the unnessary attributes for data reduction | Finding relationship of entities sharing large no. of relationships | forming the child entity for the encoporating the extra attribute in club events and talks and workshops | no obstracles as such | no obstacles as such | no obstacles as such | no such obstracles | how the view changes when event deleted | at which point the registration is confirmed
Foram | What did you do yesterday? | Identify the enities of the application | List out the attributes of the entities | Identify the relationships between entities | Formation of complete ER diagram | Final rewiew to ER for data redudancy | Took a group review on final ER | Business Requirement for Login module | Define the organizer login module and define test cases | Finalizing the both module | Finalizing the functional requirement for the view Max. No. of registered for event module
| What will you work on today? | what are the attributes if the entities of the entities | Identify the relationships between the entities | Formation of complete ER diagram | Final review to ER-diagram for decreasing redudancy | Group rewiew on ER | Building the ER for final presentation on Visual paradigm | Define the User login module and define test cases | Finalizing the both module | Finalizing functional requirement for the view the maxno. of registered for event module
| Do you have any obstacles? | differenting the entity and functional requirements(like view can be included in entity or just a requirement) | Had to increase the entities due to multivalued attributes | At times relationships fromed loops that were to be resolved | Identifying the many to many relationships and making new entities to resolve that | no obstracles as such | no obstacles as such | confusion about the identification and rights to the user and organizer | no such obstracles | finalizing the idsa of how to check if the user is new | Lowering the complexity for the view of registered users
Dhruvil | What did you do yesterday? | identify component of diagram | Searching tools for use case and dfd | State-identify the state | State-identify transition | State diagram - find tool for drawing the state diagram | State---, and DFD- made level 0 and level 1 in tool | Finalizing State and DFD | defining requirements | defining and finalizing test case of interested club | Finalizing and writing interested club test cases in RTM
| What will you work on today? | To search tools for diagram | draw it for testing | State-identify transition | State-identifying composite state | State diagram - draw diagram in tool when receieve | finalizing State and DFD level 0 and level 1 | Requirement for modules | Test case of interested club | Finalizing and Writing the interested club module test cases in RTM | Finalizing and Writing the register for events module test cases in RTM
| Do you have any obstacles? | Are all components covered in diagram | to find which tool is proper for use case and dfd | Which processes can be state? | to take care about all transitions from initial state | No such obstacles faced | Tool related issues | No such obstacle faced | no such obstacles | No such obstacle faced | No such obstacle faced