## Sheet1
Scrum Meetings
Group -7
|  | Requirement Gathering | [9 empty] | Design | [6 empty] | Construction | [10 empty] | Testing
Person | Question | Meeting 1-17/02/20 - Requirement Gathering | Meeting 2 - 19/02/20 - Requirement Gathering | Meeting 3 - 28/02/20 - Requirement Gathering | Meeting 4 - 02/03/20 - Requirement Gathering | Meeting 5- 04/03/20 - Requirement Gathering | Meeting 6- 06/02/20 - Requirement Gathering | Meeting 7- 09/03/20 - Requirement Gathering | Meeting 8- 11/03/20 - Requirement Gathering | Meeting 9- 12/03/20 - Requirement Gathering | Meeting 10- 15/03/20 - Requirement Gathering | Meeting 11-16/03/20 - Design | Meeting 12 - 18/03/20 - Design | Meeting 13 - 20/03/20 - Design | Meeting 14 - 22/03/20 - Design | Meeting 15- 24/03/20 - Design | Meeting 16- 26/03/20 - Design | Meeting 17- 28/03/20 - Design | Meeting 18- 29/03/20 - Construction | Meetin 19- 01/04/20 - Construction | Meeting 20- 04/04/20 - Construction | Meeting 21 - 07/04/20 - Construction | Meeting 22 - 10/04/20 - Construction | Meeting 23 - 13/04/20 - Construction | Meeting 24 - 16/04/20 - Construction | Meeting 25- 19/04/20 - Construction | Meeting 26- 22/04/20 - Construction | Meeting 28- 02/05/20 - Construction | Meeting 29- 03/05/20 - Construction | Meeting 30- 04/05/20 - Testing | Meeting 31- 05/05/20 - Testing | Meeting 32- 06/05/20 - Testing | Meeting 33- 07/05/20 - Testing | Meeting 34- 08/05/20 - Testing | Meeting 35- 09/05/20 - Testing | Meeting 36- 10/05/20 - Testing | Meeting 37- 11/05/20 - Testing | Meeting 39- 13/05/20 - Conclusion | Meeting 40- 14/05/20 - END GAME
Muskan | What did you do yesterday? | DFD - identified inputs and outputs of the system and structured level 0 dfd | DFD- identified user processes of level 1 and relationship with user entity | DFD - Level 1 made | DFD - level 2 of organizer processes and finalized level 1 | Finalized DFD with all levels | AD - Made organizer part and add event AD | Finalized AD diagram | Test cases for 'interested club' - user requirement | Finalized interested club module test cases requirements | Finalzed test cases for 'register for events' module | Finalizing Test cases for user module 2 (Requirements gathering work) | Find a reference design document and understand its key points | Started reviewing the general coding standards of products available | Found coding standard documents for Node js Chose 5 different images for 5 different clubs (illustrations) | Resolved the queries and wrote the Node js coding standards points | Finalized the React js coding standard Finalized images that will go in Add Event and Modify Event page | Drawn and Finalized the UI of Add Events page | Finalized coding standard and reviewed Design document | Reviewed design doc, brushed up the react js coding knowledge | Setted the coding environment, ensured there are no problems, refrred the Ui of Add Event module from design document | Finished the basic structure of Add Events with validation of fields and integrated with backend and db | Finished the final Add Event module with wiritng of unit test cases for the same | Written the basic structure code of Event Details and API for backend to fetch the details of the event | Finished the basic structure of Event Details and integrated with backend and db | Finished the Event Details module with proper UI | Completed the 2 independent modules - AddEvent and EventDetails and finalized the unit test cases | Completed unit testing of Event Details module and integrated the Event Card more button click with EventDeatils module | Completed the integration of modules with team with teh routing part | Completed the construction part | Found template for test cases and test plan and shared | Written Test Process and testing types and Suspension Critera in Test plan | Made the functional test cases for the system | Thorough testing was done by all | Completed the manual testing part of all the types of test (with altogether) | Fixed the major functionality bugs that came in the testing phase | Removed bugs, and did smoke and regression testing | Review all documents once for approval and verification perpose
| What will you work on today? | DFD- identifying the processs in level 1 of user | Making level 1 DFD | DFD- Remaking of level 1 after doubts and level 2 of organizer processes | DFD - finalizing the DFD | AD- Activity Diagramm - organizer part making | AD- finalizing AD | Test cases for User interaction module - select interested clubs | Finalizing 'interested user' test cases | Test cases for 'register for events' - user module 2 | Finalizing Test cases for user module 2 | Find a reference design document and understand its key points | Review the points finalized by peers and validate Start working on Coding Standard document | Start listing out points for seperate languages we use: Node js and React js Start looking for illustrations for different clubs that can go in event cards | List out coding standards in general way and in speicifc to the Node js backend framework that best suits our project structure | Listing the points for React js front end framework and Start writing the cdetaied coding standards for that. Also, look for illustrations for Add Event page, Modify Event page | Make the UI design of th Add Events module with all the fields included and color and font specififcations in the 'paint' tool. | Finalize the coding standard document and revew the design document and validate the same by discussing with peers | Reviewing the design document for the number of listings of the independent modules and dividing the work among peers | Set up the coding environment made by sumit and Start working on the individual modules assigned - Add Event module | Start coding the Add Event module part in react js | Do the proper UI of the Add Events page with image alignment and the form aligment, fields spacing and ordering, color codes etc | Start working on the second module - Event Details page | Debug the issues coming fetching data from database and Do the proper UI of the Event Details module | Do the proprt UI of Event Details with image alignment and the details aligment, fields spacing and ordering, color codes etc | Write the unit test cases for Event Details module and test it. Revise the unit test cases for the Add Event modules and finalize both | Finalize the EventDetails unit testing and communicate with team for the integration and routing of all the modules | Help in routing and integration of other modules and align all the modules CSS in same format with uniformilty | Check all the integration and routing and review all the other unit test cases and refactor my modules code with comments and intendation | Finding the correct template of Test Plan document and correct template of test cases and make excel sheet for test cases with proper template format and share with all | Divide the test plan document amongst all and review SRS & design document once before writing the test plan and write the Testing strategy and Suspension Critera | Make the Functional test cases and analyze and retrace them to requirements document and write their test step description, and expected output | Review the functional test cases and start the testing process including all | Resume the testing process and finalize the error cases in all the tests i.e. functional test, integration test and system test | Start fixing the bugs that arrived and work the Failed test cases by doing changes in the construction code | Do smoke and regression testing once after fixing UI bugs and start the testing process again (checking the failed test cases) | Go through the testing process again and test the failed test cases again and validate the UI of all the pages | Give suggestions and modifications to team members for document | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | Ambiguous nature of user and organizer as inputs to the system | No such obstacles faced | Geting data from datastore; numbers to be written on parallel processes | DFD - input and output of level 2 processes; | Online Tool related problems | doubts in forming actvity diagram of an activty | No obstacles as such for AD diagram | confusion in new user and old user interested club filling requirement, min and max number of clubs discussion | No such obstacles, doubts resolved | Any test case needed for validation status after registering; Multiple clicks register button from same user should be validated for errors? | No such obstacles faced. New phase - Design starts | Obstacles were to choose one standard document among different design documents having different formats and see and discuss what best suits our project | No such obstacles faced till now | Queries that arose were - do we need to write seperate standards for all the languages we used like in front end and back end? Do we need to write the standards for SQLITE database too? | Ostacles: it was difficult to filter out the relevant coding standards from the whole list of standard coding standards available for Node js. | Ostacles: it was difficult to filter out the relevant coding standards from the whole list of standard coding standards available for React js. | Obstacles: Validation of add event fields were confusing. Also choosing the correct image from net to be fitted into the | No such obstacles faced: New phase - construction starts | Obstacles: brushing up the React js coding framework, difficulties in figuring out the proper flow in the code, Thinking of making stubs for the assigned modules for smoke testing purposes | Obstacles: Problems in setting up the coding environment in react, installing many npm dependencies in the code and debugging the errors in the installation, memory and performance isses while using VSCode | Obstacles: | obstacles faced in finishing up the UI of the Add Events page and integratong with basic structure that incldued backend and db part | Obstacles: | Obstacles: | Obstacles: | Obstacles were faced writing the unit test cases of the EventDetails module and aligning the fields and posyer with proper CSS | Obstacles: issues were faced in integrating th event module with the event card. | Obstacles: Routing various modules generated many issues was tough to to debug every issue and find the root cause of the same (done by all) | No obstacles as construction phase is over. Test plan query: Suspension Criteria content | Test Plan subpoints queries: 1. Difference between test cases and unit test cases, 2. Need to document Smoke testing or not, 3. which test approach should be used among all | No such obstacles in test plan part. Queries in functional test cases: How are unit test cases different than functional test cases? | No such obstacles now Query related to testing process: should the google sign in password validation be considered in our functional testing? | Obstacles faced were to divide the testing part among all. Ambiguity in one of the functional test cases - likes event (not in srs but in diagrams) | No obstacles faced till completion of testing. Bugs that arrive: 1. The content of view events tabs is shown after clikcing it on more than 3 times. 3. Performace and security issues are not validated as product is not deployed yet. (System testing remains) | Major Bugs were removed from the system. But Performace and security issues are not validated as product is not deployed yet. (System testing remains) | Obstacles: UI :the final color of the header? (logo issues) Which modules need to be selected for regression testing? Do we need to document the smoke and regression testing part? | No such obstacles faced
Arpit | What did you do yesterday? | Use case - Identify Actors | Use case - Identify use case for individual actor | State diagram - Identify the state | State diagram - identify composition state | State diagram - identify starting and endings of the states | State diagram - Draw diagram on paper | Finalizing State diagram | Define user interface module and functional requirement | Define the test cases for all the user interface requirement | Finalizing functional requirement for the view module | define test cases for give access of the screen to all user | Find a few design document for reference | Divide the parts among members for design documents | Write System Assumptions, Constraints in documentation | Write finalize System Dependencies in documentation | Finalize following diagram which decribe system correctly called Topology Diagram, External Systems Diagram, Website Architecture Diagram, Software Architecture Diagram | Draw Topology Diagram and External Systems Diagram for EventLog system in book | Draw Topology Diagram and External Systems in online tool | Started learning JavaScript | Setup all requied software for coding | Divide all modules among team members | Basic UI of 'Modify events' | Started to learn back-end for the ''Modify events'' page | Complete Functionality for Modify event | Complete the backend of 'Modify events' | Basic CSS for 'Delete event' | Complete Functionality for delete event | Check Delete and Modify event module works properly endividual |  | Find a few test plan document for reference | FInalize points for test plan document and create table of contant | Finalize all testing to be done and their schedules | Listed down all possible and require testing techniques for EventLog | Understand defination of Risk, Assumptions and Dependencies for our system | After finalizing the Risks and Assumptions discuss it with group members for approval. | After finalizing the Dependencies discuss it with group members for approval. | Review all documents once for approval and verification perpose
| What will you work on today? | Use case - Identify use case for all individual actors | Use case - Incoorporated include functionality within use cases | State diagram - Identify transition | State diagram - identify starting and endings of the states | State diagram - finalize all the state and flow of all the state transition | State diagram - send the diagram for drawing | Business Requirement for user interface |  | Business Requirement for View module | define test cases for give access of the screen to organizer | Find a reference design document | Finalize what points should be included in design document by refereing the design document found and concept taught in class | Shortlist System Assumptions, Constraints and discuss it which peers | Discuss System Dependencies with construction team and discuss the points cleared so far in documents | Find and finalize which diagram should be in design document | Search what should be in Topology Diagram and External Systems Diagram and think how they incorporate in EventLog system and draw that both diagram for EventLog system in book | Define software element and draw Topology Diagram in online tool 'draw.io' and give External Systems Diagram to Dhruvil for draw it in the tool. | Review coding standards document and start to learn JavaScript | Setup all requied software for coding and review the requirement document and design document once | Divide all modules among team members | Basic UI of 'Modify events' from 'Add event' page | Complete the proper UI for the 'Modify events' and start to learn backend for the same | Complete the backend of 'Modify events' and start the basic UI of 'Delete event' | Write SQL quieiries for modify details of the event in database | Delete event functionality only for organizers | Integrate Delete functionality for organizers only. | Write SQL quieiries for deleting events from database | Finalize and verify all functionality of modify event and delete events and combine the module with final main code | Find a reference documents for test plans | Finalize what points should be included in test plan document by refereing the test plan document found and concept taught in class and distribute among all | Divide the topics and sections among members and finalize schedulles for testing | Find All endividual testings perpose and why it is important | Understand all Risks, Assumptions and Dependancies in EventLog system | Finalize all Risks and Assumptions for our system. | Find out all Dependencies for EventLog system. | Finalize all Functional Test Reiviews with Group members. | Give suggestions and modifications to team members for document | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | Use case - Can event be the Actor? | Use case - can backgroud process part of the use case | Can background process be state? | How to handel state backward compatibility | No such obstacles faced | No such obstacles faced | User can access system in any plotform | No such obstacles | Problem of diffrentiate screen user and organizer | No such obstacles | No such obstacles faced | It have been very tough to decide what factors define the design document correctly | Which points comes under which part? | No such obstacles | How many and which diagram should decribe the system correctly? | No such obstacles | No such obstacles | No such obstacles | No such obstacles | No such obstacles | Doubt regarding which details can be modify and which should not be modify | No such obstacles | No such obstacles | No such obstacles | All club organizers can delete the event | No such obstacles | No such obstacles | No such obstacles | No such obstacles | It have been very tough to decide what factors define the test plan correctly | No such obstacles | How many and which testings should be included | How to define Risks, Assumptions and Dependancies for our system | No such obstacles | No such obstacles | No such obstacles | No such obstacles
Vaishwi | What did you do yesterday? | Use case - Define the Scenario | Use case - Incoorporated include functionality within use cases | Use case - Finalizing remianing thing | Use case cmpleted in tool | AD - Made user part diagram | AD - made AD of modify and delete events | finalizing AD | Define the User login module and define test cases | Define the organizer login module and define test cases | Finalizing all requirement for the view module | define test cases for give access of the screen to all user | Find a few design document for reference | Finalize what points should be included in design document | Written Intended Audience, Key Stakeholders, Languages and Tools in the design document and also mention which design document we refered | Written what is current method and proposed method for convey the event message in design document | Finalize 4 diagram which decribe system correctly called Topology Diagram, External Systems Diagram, Website Architecture Diagram, Software Architecture Diagram | Draw Website Architecture Diagram and Software Architecture Diagram for EventLog system in book | Draw Software archiecture diagram and website architecture diagram in online tool | Brush up the coding knowledge of react js | Setup the system compability for coding, review the requirement document and design document once | Define independent module and divide among all | Basic UI of 'Select interested club' | Complete the proper UI of 'Select interested club' and start the backend of 'Select interested club' | Complete the backend of 'Select interested club' | Basic UI of 'Register for event' | Complete the UI of 'Register for event' and start the backed of 'Register for event' | Complete backed of 'Register for event' | List the module which are other module which wil comunicate with 'Select interested club' and 'Register for event' | Create the definition of done document | Find a few test plan document for reference | FInalize points for test plan document and create table of contant | Written test approach in test plan document | Define entry and exit criteria for EvetLog system | Written entry and exit criteria in test plan document | Define 3 test case : Integration test case, Functional test case, system test case | Written Integration test case in test case document | Review all documents once for approval and verification perpose
| What will you work on today? | Use case - Identify Actors | Use case - Finalizing remianing thing | Use Case- Draw diagram in the online tool | AD- Activity Diagramm - user part making | AD- expanding modify/delete events into new activty diagram | AD - finalizing AD | Business Requirement for Login module | Define the organizer login module and define test cases | Functional reuirement for View module | define test cases for give access of the screen to all user | Find a reference design document | Finalize what points should be included in design document by refereing the design document found and concept taught in class | Write Intended Audience, Key Stakeholders, Languages and Tools in the design document and also mention which design document we referd | Write what is current method of delivering the message of any event happens at ahmedabad university and what are we proposed for that in design document | Find and finalize which diagram should be in design document | Search what should be in Website Architecture Diagram and Software Architecture Diagram and think how they incorporate in EventLog system and draw that both diagram for EventLog system in book | Define software element and draw Website architecture diagram and software architecture diagram in online tool 'draw.io' | Review coding standards and brushup the coding knowledge of react js | Setup the system compability for coding, review the requirement document and design document once | Define independent module and divide among all | Basic UI of 'Select interested club' | Complete the proper UI of 'Select interested club' and start the backend of 'Select interested club' | Complete the backend of 'Select interested club' | Basic UI of 'Register for event' | Complete the UI of 'Register for event' and start the backed of 'Register for event' | Complete backed of 'Register for event' | List the module which are other module which wil comunicate with 'Select interested club' and 'Register for event' | Create the definition of done document | Find a reference documents for test plans | Finalize what points should be included in test plan document by refereing the test plan document found and concept taught in class and distribute among all | Review the requirement document and search about the test approach which we will going to follow and write test approach in test plan document | Understand the entry and exit criteria, define entry and exit criteria for EventLog system | Write entry and exit criteria in test plan document | Understand all test case taught in class and Decide which type of test case we have to done for EventLog system | Search about Integration test case and write Integration test case in test case document | Search about Function test review document and preapare Functional Test Review document and verfity checklist of definition of done document | Give suggestions and modifications to team members for document | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | Take care of each small requirement | No such obstacles faced | No such obstacles faced | ,No such obstacles faced | doubts in making multiple activity diagrams | doubts in forming actvity diagram of an activty | User includes which student and staff both | No such obstacles | Give access of the screen view to all user and organizer | No such obstacles | No such obstacles faced | It have been very tough to decide what factors define the design document correctly | No such obstacles | No such obstacles | Very tough to decide how many and which diagram should decribe the system correctly | No such obstacles | No such obstacles | No such obstacles | No such obstacles | No such obstacles | No such obstacles | No such obstacles | Doubts how many club we have to allow to select | No such obstacles | Dounts regarding paid and free events | Doubts regarding registration link in case of paid and free events | No such obstacles | No such obstacles | No such obstacles | It have been very tough to decide which type of testing we should have to include | Decide which testing statergy define the best for EventLog system |  | No such obstacles | Doubts in Regression testing | No such obstacles | Doubts regrading Functional test reviews | No such obstacles
Sumit | What did you do yesterday? | Made level 0 dfd and researched on number of levels of dfd | Identified organizer processes of level 1 and relationship with organizer entity | Made Level 1 DFD | Level 2 of user processes | made Level 2 for organizer processes | Validation of DFD | Finalizing DFD | defining organizers interaction | definined the working of modifying an event | defined viewing registered users for event | define test cases for give access of the screen to all user | Find a few design document for reference | Divide the parts among members for design documents | Write System Assumptions, Constraints in documentation | Write finalize System Dependencies in documentation | Finalize following diagram which decribe system correctly called Topology Diagram, External Systems Diagram, Website Architecture Diagram, Software Architecture Diagram | Draw Topology Diagram for EventLog system in book | Finalized Topology Diagram for defined software elements | created basic login structure in ReactJS | finalized auth app | created login page ui | finalised login | finish routing for MPA | finalize queries for api | finish POST, GET APIs for clubs. | finished functionalities | finish routing | finish ui |  | Find a few test plan document for reference | FInalize points for test plan document and create table of contant | Discuss Functional testing understading with group member. | Create table with the functional testing content | Done with all possible test reviews. | Understand defination of Risk, Assumptions and Dependencies for our system | After finalizing the Risks and Assumptions discuss it with group members for approval.
| What will you work on today? | Identifying the user processs in level 1 of organizer | Making level 1 DFD | Level 2 user process - view events, authorize user | Level 2 organizer process - add,modify,delete events | review and validate Level 2 DFD | Build DFD on Visual Paradigm Tool | designing the attributes to fill while adding an event, if any entry field is empty | while modifying if more than one field is changed | viewing the number of registrations after event modification | Finalize view of registered users | Find a reference design document | Finalize what points should be included in design document by refereing the design document found and concept taught in class | Shortlist System Assumptions, Constraints and discuss it which peers | Discuss System Dependencies with construction team and discuss the points cleared so far in documents | Find and finalize which diagram should be in design document | Search what should be in Topology Diagram and think how they incorporate in EventLog system and draw that both diagram for EventLog system in book | Define software element and draw Topology Diagram in online tool 'draw.io' | Set up Devlopment Environment on vscode with ReactJS | Set up Google Developer Console for authorization. Created Google OAuth web client IDs. | Setup google SDK modules in react. create restricted authorization client | authorize with backend and set up browser localstorage for cookies | setup protected routing for available modules with react-router. | setup backend api for fetching available club selections | setup cors security in ExpressJS backend API | Setup API calls in frontend | setup redirections for mainpage,clubs based on new users | use material-ui components for final ui | ... | Find a reference documents for test plans | Finalize what points should be included in test plan document by refereing the test plan document found and concept taught in class and distribute among all | Find the documents for Functional Test Review for reference | Define all possible Functional review from system by refering referenvce documents | Discuss with construction team for approval and functional testing | Understand all Risks, Assumptions and Dependancies in EventLog system | Finalize all Risks and Assumptions for our system. | Find out all Dependencies for EventLog system. |  | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | No such obstacles faced | organizing level 1 structure | Representing different category of events and conditional statements in DFD | Representing different views of different category of events in DFD | No such obstacles faced | Tool related issues | No such obstacles | no such obstacles | flow of updating modified events to users | changing views of registered users in case of modification or cancelation | No such obstacles | It have been very tough to decide what factors define the design document correctly | Which points comes under which part? | No such obstacles | How many and which diagram should decribe the system correctly? | No such obstacles | No such obstacles | No such obstacles | learning developer console | SDK API calls | using newer localstorage instead of tokens | redirections and props passing for different pages | no such obstacles | cors restrictions | no obstacles | router obstacles | no obstacles | no obstacles | No such obstacles | It have been very tough to decide what factors define the test plan correctly | No such obstacles | No such obstacles | How many functional test reviews should need? | No such obstacles | No such obstacles | No such obstacles
Krinali | What did you do yesterday? | Identify the enities of the application | List out the attributes of the entities | Identify the relationships between entities | Formation of complete ER diagram | Final rewiew to ER for data redudancy | Took a group review on the final ER | Completing the ER | defining organizers interaction | defining the working of adding the event | defining the working of deleting the event |  | documenting the purpose of the design document in the file | worked on identification for the design document | worked on scope | worked on general overview of EventLog | worked on logo and the goals and guidelines | worked on Development Methods & Contingencies | Finalized the logo and completing business requirements | Design the UI interface using CSS for clubwise events | worked on basic structure of the page | worked on module | completed the clubwise event page | started work on added events page | made basic layout for the added evnts page | worked on the clubwise event view page | completed the module | worked on layout of the added events page | worked on added events page ui and module |  |  |  | made the cases and finalize the testing | started the testing process | worked on test cases | completed the alloted test cases | worked on the bugs
| What will you work on today? | what are the attributes if the entities of the entities | Identify the relationships between the entities | Formation of complete ER diagram | Final review to ER-diagram for decreasing redudancy | Group rewiew on ER | Building the ER for final presentation on Visual paradigm | building template for adding event, display on screen | while modifying if one of the field is changed | if event deleted and no reason provided |  | worked on documenting the purpose of the design document and templetes for the logo | work on the identification for the design document | Listing the points for a scope of the project : justification, constrains,asumptions which were discussed by the group. | Documenting a general overxview of EventLog . | Listing the possible logo designs and work on the goals and guidelines for the design considerations | work on Development Methods & Contingencies | work on the logo design and finalize it and list down business requirements and documenting user interface designs | UI are finalized. Set up the environemnt for coding the ui. | setting up environment | complete the module in js | completing the finalize design for clubwise events, define the decided standards of design from color to font | work on the page for added events page | create the basic structure of the page | incorporate the page with the layouut decided for the page. the color code, theme,positions | work on the module for the same page | work on the added events page structure | set the layout as per the dcided layout, standard and theme/ start on module | complete the module for fetching data and doing the tasks. revise both pages and list down the possible test cases | Work on the templete for the testing documentation | finalising the contents and dividing the wok | review the other documents and deine a strategy | working on the test cases for the parameters | listing down test cases outputs and what is thr nature of output | list down all the cases and document them | list down the errors/ problems in the nature of the output of every case and work on them | worked through the problems |  | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | identifying weak and strong entities | Removed the unnessary attributes for data reduction | Finding relationship of entities sharing large no. of relationships | forming the child entity for the encoporating the extra attribute in club events and talks and workshops | no obstracles as such | no obstacles as such | no obstacles as such | no such obstracles | how the view changes when event deleted | at which point the registration is confirmed |  |  | The challenge was to make the scope relevant, achieveable and specific. Documenting it in those terms was a challenge | Listing each and every major parameters of the software along with listing down the major assumptions and a border | as for logo deciding the color paletee and the theme was a task. As for goals listing down the specification as per the architecture , environment , APIs required a lot of drafts | challenge was to accomodate the methods and contingencies which are possible for the system by considering every scenario |  | Rebrusing tthe coding methods | working way through css |  | Setting up the stadards to match with decided design |  | setting up every minute detail of the page and loction f parameters |  | setting up the details as per fetched from database | fetching the data and showing it in the manner required |  |  |  | working the way through every parameter | finding a suitable strategy for testing | including only those testing cases which actually help in going through the software | testing the process with every possible kind of entry possible | considering every scenario | comparing the desired output with the ones actually got | locating the error reason and finding a solution to get the desired output
Foram | What did you do yesterday? | Identify the enities of the application | List out the attributes of the entities | Identify the relationships between entities | Formation of complete ER diagram | Final rewiew to ER for data redudancy | Took a group review on final ER | Business Requirement for Login module | Define the organizer login module and define test cases | Finalizing the both module | Finalizing the functional requirement for the view Max. No. of registered for event module | With help of krinali did found the format of the design document | Worked on designing the goals and guidlines for the project | Work on the mobility and scability of and the development environment | Work on the point : open API centric and performance engineering | Work on Operational Envirnonment | Work on the database design | Work on the database design | Design the UI interface using CSS for Login and Interested clubs | Determine the risk factors in the project for requirement | Determine and list the risk factors of the elicitations phase | Design the page events for me | Complete the coding for the page events for me | Due to syntax and some logical errors had to continue with page events for me | Start designing the registered events view | Part of coding for the registered events view | Complete the coding of registered events view | Search for a solution to view paid event's registerations | Worked on the integration of the pages done by me | Work for the testin documentation templete | Finalizing the commponents to be included in the testing document | Worked on the points that defines the purpose of the testing | Work on the scope of testing analysing all the modules to be tested | Work on part of the scope with defining all the functions to be tested | Worked on the functionalities that need not to be tested | Work on generating the test scenarios with aussumptions of the functions that cannot be tested whitebox | Worked with the added functions that had to be incoporated for the failed test cases of functionalities done by me | Review of all the documentation and check the final functionality with the original requirements list
| What will you work on today? | what are the attributes if the entities of the entities | Identify the relationships between the entities | Formation of complete ER diagram | Final review to ER-diagram for decreasing redudancy | Group rewiew on ER | Building the ER for final presentation on Visual paradigm | Define the User login module and define test cases | Finalizing the both module | Finalizing functional requirement for the view the maxno. of registered for event module | Start the wok on design document | Work on the distributed partr of the design document | Work on project mobility scalibility platform and development environment | Work on the point :open API centric and performance engineering | Work on Operational Environment | Working on the database design | Work on the database design | Design the UI interface using CSS for Login and Interested clubs | Determine the risk factors in the project for requirement | Detemine and list the risk factors for the elicitation phase | Design the page view events for me | Complete the coding of the page events for me | Start the designing registered events view | Start the designing registered events view | Complete the coding for the registered events coding | Complete the coding of the registered event view | Search for a solution to view paid event's registerations | Worked for the integration of the pages done by me | Work for templete for testing documentation | Finalizing the componenets to be included in the tesing document | Wroking with the points to included in the purpose and scope | Work on the scope of testing | Work on the scope of testing functions to be tested | Work on the scope part functionalities not to be tested | Work on generating the test scenarios with aussumptions of the functions that cannot be tested whitebox | Worked with the added functions that had to be incoporated for the failed test cases | Review of all the documentation and check the final functionality with the original requirements list |  | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | differenting the entity and functional requirements(like view can be included in entity or just a requirement) | Had to increase the entities due to multivalued attributes | At times relationships fromed loops that were to be resolved | Identifying the many to many relationships and making new entities to resolve that | no obstracles as such | no obstacles as such | confusion about the identification and rights to the user and organizer | no such obstracles | finalizing the idsa of how to check if the user is new | Lowering the complexity for the view of registered users | Many formats of design documentation were available had to select most relevent | bit difficulty in finalizing the final goals and guidlines of the project as there are many to condsider but can incoporate a few due to the time and resources constraint | No obstracles as such | Understanding the performance engineering that AWS provides | Finalizing the operational environment requires the comparision of various technologies available and check the technologies that fit the requirements of the project | The database design for the final project needed many changes based on the page requirements so requires the complete flow of the program with each data passing parameters | Through the project needed to incoporate the changes | Picking the rignt frames and colors and all contributes a lot to the project look and overall user interface | The risks the were encountered may not have been encountered during the initial design phase so this might mislead the project | Same that were stated before | Had to make small changes from the original design of the UI to reduce some complexity | Syntax errors other than that no issues as such | Had to research a lot for the last logical error | No issues as such | Faced a problem for paid events' registration cannot be viewed came to the solution of keeping the paid events off the charts as of now | Other than the previous no major obstracle | No solution found to prev problem | Integration needed to change some parameters and integration erroes | No obstracles as such | In components which testing tecniques to be incoporated and which testing procedure to be followed | Testing of any softeare is an obvius purpose to find the unfound purposes took a lot time | Had to look into all the components that needed to be tested | Had to define some testing functionality with both organizer and user perspective | Search the functions that require rigour testing while development and some functions cannot be tested with white box can only perform blackbox testing | Had to make assumptions that the module might be following certain procedures | There were not major failed tests as such so no obstarcles | Made some changes in the final documents due to technical requirements and some other changes
Dhruvil | What did you do yesterday? | identify component of diagram | Searching tools for use case and dfd | State-identify the state | State-identify transition | State diagram - find tool for drawing the state diagram | State---, and DFD- made level 0 and level 1 in tool | Finalizing State and DFD | defining requirements | defining and finalizing test case of interested club | Finalizing and writing interested club test cases in RTM | Writing register for event module test cases in RTM | find reference document and its key points | Understanding key points | Found illustration for login page | Referred the report | Finalized the report after formatting report | Completed design document | Found tools and draw the external system diagram | Started searching about react js | Learning react js | Implemented examples and learnt react js | Connect with back end by setting environment | learnt about code structure | Learnt about usage of module | Implement various examples of that module | implementation of module and to set contents and width | worked on layout of the module | worked on ui and module | completed construction part | Worked on test plan template | finalizing testing tools for test cases and writing it to test plan | finalizing and writing it to test plan | made the test cases for testing | started testing process | found output of test cases | List down test cases with output and also document all test cases
| What will you work on today? | To search tools for diagram | draw it for testing | State-identify transition | State-identifying composite state | State diagram - draw diagram in tool when receieve | finalizing State and DFD level 0 and level 1 | Requirement for modules | Test case of interested club | Finalizing and Writing the interested club module test cases in RTM | Finalizing and Writing the register for events module test cases in RTM | Searched for reference document | Understand its points | Searching illustration for login page | Reviewed node js coding standard | Formatted the report | Helped members in design document | Searched online for tools to draw external system diagram | Finalized diagram by showing it to team | Started learning react js | Started implementing examples of react js | Started learning on how to connect with back end | Saw work of construction and reviewed it and see how the code composition works | Search about use of container module | Implement example of that module | Implemementation of module for our site | work on layout of module and also its structure | set the layout of module | completed ui and also functionality | worked on test plan template | search and define testing tools for creation , reporting , tracking , execution | search and define environment for testing | writing glossary to test plan document | Finalize the testing and also set parametes of test cases | find output of test cases | Complete output of all test cases | Completing remaining parts of test plan document |  | Congratulate to all team members for successfully completed project
| Do you have any obstacles? | Are all components covered in diagram | to find which tool is proper for use case and dfd | Which processes can be state? | to take care about all transitions from initial state | No such obstacles faced | Tool related issues | No such obstacle faced | no such obstacles | No such obstacle faced | No such obstacle faced | No such obstacle faced | No such obstacle faced | No such obstacles | Are all things covered or not | No such obstacled faced | No such obstacles | Are all components of diagram present there | No such obstacle faced | Installing software for react js | Running examples and installing library | Environment and server | No obstacles faced | No such obstacle | setting environment | Setting paramter and environment | settings of details are proper or not | No such obstacle | No such obstacle | No such obstacles | Finding best tools | finding best environment for testing | No such obstacles | No such obstacles | testing with each kind of entry | No such obstacles | No such obstacles